## Sheet1
| Key |  | Activity on track
Activity delayed
Activity rescheduled
|  | 2023-06-04 | Deadline or date of activity
Y1
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Owner of activity | Notes
Activity | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Resource Library
Equip library with books | [12 empty] | Librarian
Buy computer | [12 empty] | Secretary
Resource use training |  |  |  | 2023-01-15 | [6 empty] | 2023-08-11 |  | Librarian
Curriculum revision
Industry secondments | [12 empty] | Staff
Report due from secondments | [5 empty] | 2023-03-25 | [6 empty] | Staff
Stakeholder meetings |  |  |  |  | 2023-02-20 |  |  | 2023-05-02 |  |  | 2023-08-02 |  | Project lead
Preparation for approval | [11 empty] | Print 15-Sep | All team